## Sheet1
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header, carousel, booking, categories | 2022-04-06 | 2022-04-06 | 100% | vhhoang | 2022-04-06 | 2022-04-06 | 95% | vhhoang
Header, Carousel, Jumping, Blog, Testimonials, Footer | 2022-04-05 | 2022-04-05 | 100% | vmcuong | 2022-04-05 | 2022-04-05 | 95% | vmcuong
Updated video link | 2022-04-11 | 2022-04-11 | 100% | vhhoang | 2022-04-11 | 2022-04-11 | 100% | vhhoang
minor header background change, add responsive for header text,fixed booking__right overflow, add some change to video modal | 2022-04-12 | 2022-04-12 | 100% | vhhoang | 2022-04-12 | 2022-04-12 | 100% | vhhoang
edited responsive for categories | 2022-04-13 | 2022-04-13 | 100% | vhhoang | 2022-04-13 | 2022-04-13 | 100% | vhhoang
added initial js for light/dark mode | 2022-04-14 | 2022-04-14 | 50% | vhhoang | 2022-04-14 | 2022-04-14 | 100% | vhhoang
finished initial js for light/dark mode, changed position for video play button, minor changes to blog and testimonial sections | 2022-04-14 | 2022-04-14 | 100% | vhhoang | 2022-04-14 | 2022-04-14 | 100% | vhhoang
fixed video position | 2022-04-15 | 2022-04-15 | 100% | vhhoang | 2022-04-15 | 2022-04-15 | 100% | vhhoang
fixed padding for video section, fixed video play button position, modified modal position for video, added responsive for modal video | 2022-04-16 | 2022-04-16 | 100% | vhhoang | 2022-04-16 | 2022-04-16 | 100% | vhhoang
Updated whole js | 2022-05-02 | 2022-05-02 | 100% | vhhoang | 2022-05-02 | 2022-05-02 | 100% | vhhoang